# Project Definition Example

## Objectives & Success Criteria

Improve student retention by 5% through better attendance data. Success = system fully operational by Sept 2025.

## Scope (In/Out)

In: Lecture/seminar attendance monitoring. Out: Exam attendance.

## Governance & Team Structure

Sponsor: Director of Student Services; PM: Senior IT Project Manager; Stakeholders: Registry, Faculties.

## RAID Log Setup

Risks logged in RAID Excel template. Example: Vendor integration delays.

## Estimated Costs & Benefits

Costs £120k; Benefits: improved compliance, reduced manual workload, improved retention.

## Stakeholder Approvals

Signed by Sponsor, Registry, Faculties.