## Sheet1
ID | Type (Risk/Assumption/Issue/Dependency) | Description | Impact | Likelihood | Owner | Mitigation/Response | Status
1 | Risk | Integration delays with timetabling system | High | Medium | IT Project Manager | Supplier engagement and testing plan | Open
2 | Dependency | Data feeds from SITS must be available | Medium | High | Registry | Confirm availability early | In Progress